## Annual Workplan
Participatory Responsive Governance - Principal Activity (PRG-PA) Program
Program Purpose: Improve collective (government and citizen) responsiveness to priority public needs
Project Activities | Organization Responsible |  |  | Period
Year 1
|  | 2016 | [10 empty] | 2017
|  | February | March | April | May | June | July | August | September | October | November | December | January
Program start up
Meetings /collaboration with LASDEL/ODI on Political Economic Analysis (PEA) research findings | CPI
Establish PRG-PA consultation committee | CPI
Coordination meetings with donors and implementers | CPI
Conduct baseline evaluation | CPI
Coordinate with AidData for impact evaluation | CPI
Meetings with INGOs to identify opportunities for collaboration and coordination in Diffa, Zinder and Agadez | CPI
Meetings with local authorities and key local actors to identify areas of intervention in Diffa, Zinder and Agadez | CPI
Determine specific areas of intervention for program activities | CPI
Discussions with researchers (from ODI/LASDEL, Afrobarameter etc.) on diffusion of PEA research | CPI
Recruit national staff | CPI
Program Introduction Event Regional | CPI
Organize and host PRP-PA monthly program coordination meetings | CPI
Outcome 1: Elections are more responsive to priority public needs
1.1 Convene election donors and implementers to share citizen priorities
Organize meetings with international donors and implementers to review and discuss citizen priorities | CPI
1.2. Conduct workshop for civil society and government representatives on evidence-based, non-partisan advocacy
Organize workshop for CSO representatives on evidence-based, non partisan advocacy | CPI
1.3. Support media coverage of local elections
Develop the format and content of radio programs in collaboration with media partner | Equal Access (EA)
Partners' radio stations broadcast-local election debates | Equal Access
Focus/Listening Discussion Groups | Equal Access
Partners' radio stations produce call-in and chat shows on citizens' priorities | Equal Access
Hold listening groups to listen and discuss political party debates | Equal Access
Support creation of radio programs (call-in shows, public service announcement, radio magazine, etc.) addressing priorities | Equal Access
Media partners produce media-stakeholder public dialogues | Equal Access, AEC
1.4. Facilitate issue-based multi-stakeholder dialogues for local elections
Dissemination workshop of citizen priorities and action steps at regional level in Niamey, Diffa, Zinder and Agadez | CPI
Conduct local (communal and regional) consultation around citizen priorities | CONGAFEN, RAIL, AEC
Use IVR/SMS platforms to gather additional citizen priorities and concerns to inform party questionnaires | CONGAFEN, RAIL, AEC, EA
Support and facilitate communal level multi-stakeholder public dialogues | CONGAFEN, RAIL, AEC
Three day finance and compliance workshop for pre-selected CSOs sub-grantees | CPI
Provide technical assistance to pre-selected CSO sub-grantees | CPI
One communal level political party pre-debate in each target commune and chef-lieu of region | CONGAFEN, RAIL, AEC
One communal level political party debate in each target commune and chef-lieu of region | CONGAFEN, RAIL, AEC
1.5. Conduct civic education campaign on code of conduct and conflict mitigation
Develop civic education materials including posters and media messages on conflict mitigation and code of conduct | EA, CONGAFEN, RAIL, AEC
Conduct TOT training for civic educators
Trained civic educators conduct civic education
Support participatory theater around conflict mitigation
Outcome 2: Informed multi-stakeholder (government and non-government) contribution to specific elements of reform implementation for targeted citizen priorities
2.1. Conduct government systems mapping to inform collective action initiatives
Create and share tactical government systems maps | CPI
2.2. Build cadre of master dialogue facilitators
Consultations with FLAG International and others to identify CSOs and gauge involvement | CPI
Issue a solicitation for CSOs for public dialogue RFA | CPI
Conduct public dialogue design workshops | CPI
Receive proposals and shortlist CSOs | CPI
Prepare and execute sub-grants with USAID approval | CPI
Organize master dialogue facilitators public dialogue facilitation workshop | CPI
2.3: Broker commitments around targeted citizen priorities through local partner dialogue
Organize multi-stakeholder dialogues with diverse actors to identify shared goals, leverage resources, and build strategic partnerships with other stakeholders at various levels | CONGAFEN, RAIL, AEC
Organize communal level discussions with key actors around citizen priorities on education, health and security and build collective action | CONGAFEN, RAIL, AEC
CSOs organize quarterly regional dialogue sessions around successes and challenges in building support for policy reform and engaging with regional representatives about shared priorities | CONGAFEN, RAIL, AEC
EA’s network listening groups create discussions among youth regarding priority health, education and security initiatives in conjunction with other dialogue events | Equal Access
Invite citizens in target communities to participate in dialogues via SMS, IVR, and other social media | Equal Access
2.4: Support media production of reliable information that supports collective action
Conduct workshops for journalists and media professionals at the national and local levels on effective interview and discussion techniques to use with with citizens, elected leaders, and political party representatives around priority issues | Equal Access
Training on factchecking information to ensure accuracy of reporting and to ensure that information reported to citizens is accurate | Equal Access
Broadcast weekly, 30-minute radio magazine with roundtable discussions, citizens interviews, and guest interviews | Equal Access
Coordination meetings
Quality, Monitoring
Draft and submit PMP and workplan to USAID | CPI
Activity quality assessment and monitoring | CPI